## Action items
Action item | Owner | Due date | Status | Source meeting | Notes
Send revised project timeline | Maya Chen | 2026-10-02 | In progress | Project kickoff ? 2026-09-28 | Include two review milestones
Confirm the launch review attendees | Luis Patel | 2026-10-01 | Not started | Project kickoff ? 2026-09-28 | Check with design and support leads
Share the customer FAQ draft | Nia Brooks | 2026-10-05 | Not started | Project kickoff ? 2026-09-28 | Flag questions that need approval
Approve the final launch checklist | Maya Chen | 2026-10-07 | Not started | Project kickoff ? 2026-09-28 | Review after FAQ comments are resolved
Send support team briefing | Luis Patel | 2026-10-09 | Not started | Project kickoff ? 2026-09-28 | Include escalation contact and release date