## Account review
Account | Review period | Customer priority | Agreed goal | Progress and evidence | Work completed | Open action | Owner | Due date | Risk or blocker | Decision needed | Next-quarter plan | Customer feedback | Follow-up owner | Follow-up date
Northstar Analytics | Q2 | Shorten weekly reporting preparation | Reduce process from 4 hours to 2 hours weekly | Customer estimates 2.5 hours; baseline to confirm | Workflow launched for one team | Confirm baseline and method | Operations lead | July 2 | Second-team access awaits internal approval | Sponsor to decide on expansion after baseline check | Validate time saved and review second-team rollout | Requests shorter monthly status summary | Customer success manager | June 19
Acme Studio | Q2 | Keep campaign approvals on schedule | Agree review turnaround with stakeholders | Two approvals remain open; verify dates with client | Campaign plan reviewed | Name backup approver | Marketing director | July 8 | Approver unavailable in late July | Confirm revised review dates | Review approval flow and campaign milestones | Wants one consolidated request list | Account lead | June 24
Pine & Co. | Q2 | Prepare a second team for rollout | Complete readiness review before expansion | Training plan drafted; attendance not confirmed | Admin session held | Confirm training attendees | Customer administrator | July 5 | Training dates conflict with staff leave | Select a new training date | Check readiness and agree rollout decision | Asked for shorter training materials | Customer success manager | June 20
Harbor Works | Q2 | Improve handoff between teams | Agree handoff owner and required fields | Draft process reviewed by both team leads | Required fields documented | Approve handoff checklist | Operations manager | July 1 | Ownership differs by region | Decide regional owner model | Review use of checklist and unresolved gaps | Wants clearer escalation steps | Account lead | June 19
Maple Health Group | Q2 | Reduce duplicate status requests | Use one agreed channel for weekly updates | Update format proposed; adoption not yet checked | Weekly summary outline shared | Choose update owner | Program lead | July 10 | Two teams still send separate requests | Approve a shared update format | Check whether the shared format helps | Prefers a brief summary with links | Customer success manager | June 21