## Weekly status
Project or workstream | Reporting period | Overall status | Progress this week | Next steps | Owner | Blocker or decision needed | Due date | Change since last update
Website launch ? checkout | Sep 21?25, 2026 | Yellow ? review date at risk | Payment test passed on staging | Complete accessibility review | Jordan Lee | Legal approval needed; Priya to confirm | Sep 29, 2026 | Review moved to Oct 2
Client onboarding ? Northstar | Sep 21?25, 2026 | Green ? on plan | Kickoff completed; access confirmed | Send first-week plan | Maya Chen | None this week | Sep 28, 2026 | No change
Quarterly reporting ? analytics | Sep 21?25, 2026 | Red ? data dependency | Defined required metrics | Confirm source data owner | Luis Patel | Data export delayed; director decision needed | Sep 30, 2026 | Milestone at risk
Support help center | Sep 21?25, 2026 | Green ? on plan | Reviewed 12 draft articles | Publish approved articles | Nia Brooks | None this week | Oct 1, 2026 | Two articles added
Mobile checkout | Sep 21?25, 2026 | Yellow ? testing in progress | Fixed address validation issue | Retest edge cases | Priya Shah | Waiting for test account | Sep 29, 2026 | Retest date unchanged