# Weekly status update

Use one concise update per project or workstream. Replace the example content with confirmed information before sharing.

## Project or workstream

[Project name and area]

## Reporting period

[Start date ? end date]

## Overall status

[Green / yellow / red ? reason]

## Progress this week

[Completed work or milestone]

## Next steps

[Action ? owner ? due date]

## Blocker or decision needed

[What is blocked, who can help, and by when; or None this week]

## Change since last update

[New risk, scope change, or date change]

# Filled-in example

Project: Website launch ? checkout | Reporting period: September 21?25, 2026

Overall status: Yellow ? launch review may move if legal approval is late.

Progress: Payment testing passed on staging. Support reviewed the revised help text.

Next steps: Jordan Lee completes accessibility review by September 29. Priya Shah confirms legal approval by September 28.

Blocker: Final approval for refund wording is pending. Decision needed: Can the current wording be used if approval is not in by Tuesday?

Change since last update: Review moved from September 30 to October 2 to allow time for approval.

# Async request you can copy

Please post your weekly update by [day and time]. Include progress, next steps, owners, due dates, blockers, and any decision needed. Tag the person who can help with a blocker. Flag anything that needs a live discussion.